## 710 Labs Project Breakdown
Project Name: |  | Secondary barcode and tracking flow
Client: |  | 710 Labs
Project Details:
Hourly or Flat Rate:
|  |  | 100 | Per hour
Time/Value: |  | Hours In Decimals: | Estimated Value: |  | Extras/Notes:
Project Coordination: |  | 1 | 100
Project planning: |  | 5 | 500
Planning/Quoting: |  |  | 0
| What/Scope: | 2 | 200
| Who/One/Many: |  | 0
| When/Speed: |  | 0
| Where/Touches: |  | 0
| Design/Prototype: | 2 | 200
| Add/Insert: |  | 0
| Edit/Update: |  | 0
| View/Show/Report: | 2 | 200
| Export: |  | 0
| Send/Transport: |  | 0
| API/Socket: |  | 0
| Manual/Automatic: |  | 0
| Documentation: | 2 | 200
| Client Interactions: |  | 0
| Quoting Fee: |  | 0
0
Back & Forth w/ Client: |  | 2 | 200
Collect Monies: |  |  | 0
Adilas - Move to Project Q: |  | 1 | 100
Assign To Developer: |  | 2 | 200
Project Management: |  | 10 | 1000
Build It/Dev Time: |  |  | 0
| Review: |  | 0
| Plan: |  | 0
| Develop: | 81.5 | 8150 |  | see 710 Labs - time id 1599 tab
| Q & A - Loop: | 5 | 500
| Testing - Loop: | 5 | 500
Code Sign-Off - Loop: |  | 5 | 500
Merge & Deploy: |  | 2 | 200
| Single Server: |  | 0
| Multiple Servers: | 1 | 100
News & Updates: |  |  | 0
Clean-Up: |  |  | 0
| Help Files: | 3 | 300
| Other Documentation: |  | 0
Training: |  | 2 | 200
Flex: |  | 20 | 2000
Maintenance: |  |  | 0
|  | 153.5 | 15350