## Production Enhancements
Project Name: |  | Production Enhancements
Client: |  | Molly
Project Details: |  | Add sub attributes to production
Project ID#1602
Hourly or Flat Rate:
|  |  | 100 | Per hour
Time/Value: |  | Hours In Decimals: | Estimated Value: |  | Extras/Notes:
Project Coordination: |  | 1 | 100
Project planning: |  | 1 | 100
Planning/Quoting: |  |  | 0
| What/Scope: |  | 0
| Who/One/Many: |  | 0
| When/Speed: |  | 0
| Where/Touches: | 2 | 200
| Design/Prototype: |  | 0
| Add/Insert: |  | 0
| Edit/Update: |  | 0
| View/Show/Report: |  | 0
| Export: |  | 0
| Send/Transport: |  | 0
| API/Socket: |  | 0
| Manual/Automatic: |  | 0
| Documentation: |  | 0
| Client Interactions: | 2 | 200
| Quoting Fee: |  | 0
0
Back & Forth w/ Client: |  |  | 0
Collect Monies: |  |  | 0
Adilas - Move to Project Q: |  |  | 0
Assign To Developer: |  |  | 0
Project Management: |  | 2 | 200
Build It/Dev Time: |  | 10 | 1000
| Review: |  | 0
| Plan: |  | 0
| Develop: |  | 0
| Q & A - Loop: |  | 0
| Testing - Loop: | 2 | 200
Code Sign-Off - Loop: |  | 2 | 200
Merge & Deploy: |  |  | 0
| Single Server: |  | 0
| Multiple Servers: | 1 | 100
News & Updates: |  |  | 0
Clean-Up: |  |  | 0
| Help Files: | 1 | 100
| Other Documentation: |  | 0
Training: |  |  | 0
Flex: |  |  | 0
Maintenance: |  |  | 0
|  | 24 | 2400