## Sheet 1
Project Name: |  | Add Product Type field to Parent
*Only wants this if it will tie into discount engine!
Client:
Add product type to Parent item
Project Details: |  |  |  |  | Surface in cannabis template
Project #: |  | 1775
Hourly or Flat Rate:
|  |  | 100 | Per hour
Time/Value: |  | Hours In Decimals: | Estimated Value: |  | Extras/Notes:
Project Coordination: |  |  | 0
Project planning: |  | 1 | 100 |  | Parent attribute
Planning/Quoting: |  |  | 0
| What/Scope: |  | 0
| Who/One/Many: |  | 0
| When/Speed: |  | 0
| Where/Touches: | 3 | 300 |  | Parent and cannabis template
| Design/Prototype: |  | 0
| Add/Insert: |  | 0
| Edit/Update: |  | 0
| View/Show/Report: |  | 0
| Export: |  | 0
| Send/Transport: |  | 0
| API/Socket: | 3 | 300 |  | Associate with metrc
| Manual/Automatic: |  | 0
| Documentation: |  | 0
| Client Interactions: |  | 0
| Look and feel/Mockup |  | 0
| Quoting Fee: |  | 0
0
Back & Forth w/ Client: |  |  | 0
Collect Monies: |  |  | 0
Adilas - Move to Project Q: |  |  | 0
Assign To Developer: |  |  | 0
Project Management: |  | 2 | 200 |  | Brandon time
Build It/Dev Time: |  |  | 0
| Review: |  | 0
| Plan: |  | 0
| Develop: | 6 | 600
| Q & A - Loop: |  | 0
| Testing - Loop: | 1 | 100
Code Sign-Off - Loop: |  |  | 0
Merge & Deploy: |  |  | 0
| Single Server: |  | 0
| Multiple Servers: | 1 | 100
News & Updates: |  |  | 0
Clean-Up: |  |  | 0
| Help Files: |  | 0
| Other Documentation: |  | 0
Training: |  |  | 0
Flex: |  |  | 0
Maintenance |  |  | 0
|  | 17 | 1700