## Sheet 1
Project Name: |  | surface BT apis for quote pro
Client:
Functions - init, saveResponse, login, cardLookup, saleDispense
Project Details:
Project #: |  | 1786
Hourly or Flat Rate:
|  |  | 100 | Per hour
Time/Value: |  | Hours In Decimals: | Estimated Value: |  | Extras/Notes:
Project Coordination: |  | 2 | 200
Project planning: |  | 2 | 200
Planning/Quoting: |  |  | 0
| What/Scope: | 15 | 1500 |  | api endpoints
| Who/One/Many: |  | 0
| When/Speed: |  | 0
| Where/Touches: |  | 0
| Design/Prototype: |  | 0
| Add/Insert: |  | 0
| Edit/Update: |  | 0
| View/Show/Report: | 2 | 200 |  | surface endpoints in the quote pro third party solution
| Export: |  | 0
| Send/Transport: |  | 0
| API/Socket: |  | 0
| Manual/Automatic: |  | 0
| Documentation: | 5 | 500 |  | expand on existing api documentation
| Client Interactions: |  | 0
| Look and feel/Mockup |  | 0
| Quoting Fee: |  | 0
0
Back & Forth w/ Client: |  |  | 0
Collect Monies: |  |  | 0
Adilas - Move to Project Q: |  |  | 0
Assign To Developer: |  |  | 0
Project Management: |  |  | 0
Build It/Dev Time: |  |  | 0
| Review: |  | 0
| Plan: |  | 0
| Develop: |  | 0
| Q & A - Loop: |  | 0
| Testing - Loop: |  | 0
Code Sign-Off - Loop: |  | 2 | 200
Merge & Deploy: |  |  | 0
| Single Server: |  | 0
| Multiple Servers: | 1 | 100
News & Updates: |  |  | 0
Clean-Up: |  |  | 0
| Help Files: |  | 0
| Other Documentation: |  | 0
Training: |  |  | 0
Flex: |  |  | 0
Maintenance |  |  | 0
|  | 29 | 2900