## Sheet 1
Project Name: |  | #3-enhancement to wholesale cart type |  |  | Store A is selling product wholesale to store B. They would start the cart as a wholesale cart with special cannabis permission turned on. Then when they created an invoice, this invoice wouldn’t be included in the sales push to metrc.
Client:
enhance the cart type wholesale to include a setting that will help with transfers from one corp to another.
Project Details:
Project #: |  | 1788
Hourly or Flat Rate:
|  |  | 100 | Per hour
Time/Value: |  | Hours In Decimals: | Estimated Value: |  | Extras/Notes:
Project Coordination: |  |  | 0
Project planning: |  | 5 | 500
Planning/Quoting: |  |  | 0
| What/Scope: |  | 0
| Who/One/Many: |  | 0
| When/Speed: |  | 0
| Where/Touches: | 3 | 300 |  | update gram controllers for all stores for wholesale transactions
| Design/Prototype: |  | 0
| Add/Insert: | 15 | 1500 |  | add/edit id=110 wholesale cart builder to allow for items for wholesale cart
| Edit/Update: | 12 | 1200 |  | add setting and dynamic naming to the corp wide settings page #21 for wholesale invoice
| View/Show/Report: |  | 0 |  | cascade changes.
| Export: |  | 0
| Send/Transport: |  | 0
| API/Socket: | 6 | 600 |  | condition the metrc api salesPOST to exclude wholesale invoices
| Manual/Automatic: |  | 0
| Documentation: |  | 0
| Client Interactions: |  | 0
| Look and feel/Mockup |  | 0
| Quoting Fee: |  | 0
0
Back & Forth w/ Client: |  |  | 0
Collect Monies: |  |  | 0
Adilas - Move to Project Q: |  |  | 0
Assign To Developer: |  |  | 0
Project Management: |  |  | 0
Build It/Dev Time: |  |  | 0
| Review: |  | 0
| Plan: |  | 0
| Develop: | 20 | 2000 |  | configure wholesale cart logic to include items that will be sold at cost and include rfid tags
| Q & A - Loop: |  | 0 |  | items will include sub inventory
| Testing - Loop: | 2 | 200
Code Sign-Off - Loop: |  |  | 0
Merge & Deploy: |  |  | 0
| Single Server: |  | 0
| Multiple Servers: | 1 | 100
News & Updates: |  | 2 | 200
Clean-Up: |  |  | 0
| Help Files: |  | 0
| Other Documentation: |  | 0
Training: |  |  | 0
Flex: |  |  | 0
Maintenance |  |  | 0
|  | 66 | 6600